STEAM Fair 2019 Timeline

|  |  |
| --- | --- |
| STEAM Fair Packet available on Google Classroom | FridayOctober 19, 2018 |
| STEM Fair Student & Family Information Sessions | TuesdaysOctober 23, 2018 &October 30, 2018 |
| STEAM Fair Proposal Due | MondayOctober 29, 2018 |
| STEAM Fair Feedback to Students | MondayNovember 5, 2018 |
| STEAM Fair Research Papers submitted to science teachers  | MondayNovember 26, 2018 |
| STEAM Fair Research Paper Feedback | Monday December 3, 2018 |
| Students submit and present STEAM Fair Projects in class | Wednesday - FridayJanuary 2 - 11 |
| Students Selected for STEAM Fair* Science Department will meet and go through their STEAM Fair rubrics
* Top projects in each category will be chosen to go to CMIT STEAM Fair
 | MondayJanuary 14, 2019 |
| Students and parents notified of their invitation to compete in the CMIT  STEAM Fair | WednesdayJanuary 16, 2019 |
| Labels created for STEAM Fair boards | TuesdayJanuary 22, 2019 |
| STEAM Fair Boards transported to the high school | Wednesday and ThursdayJanuary 23rd and 24th |
| STEAM Fair Boards Set up in Gym | FridayJanuary 25, 2019 |
| CMIT STEAM Fair | SaturdayJanuary 26, 2019 |